## Phase 0 — Dependency foundation

## Step 0.1

Commit title
build(ai): add core AI, resilience, and test dependencies

Goal
Prepare the project to support Spring-native AI execution, structured validation, retry/circuit breaker behavior, and deterministic testing.

Description
Update Maven dependencies only. No Java package is created yet. This commit must stay isolated because it changes the build graph and should compile before any package refactor begins.

Full and correct source

- pom.xml

Dependencies to add

- Spring AI starter for the chosen provider abstraction.

- Spring AI vector store starter only if PgVector is planned in the same phase.

- Resilience4j for retry and circuit breaker.

- Jackson/schema validation helpers for structured outputs.

- ArchUnit for dependency rules.

- Test dependencies for simulation and integration tests.

Estimated time
45 to 75 minutes

Developing language
XML

## Step 0.2

Commit title
build(ai-config): add AI properties scaffold to application configuration

Goal
Introduce centralized runtime properties before any Java implementation starts.

Description
Add empty-but-structured AI properties under the existing application configuration files. This includes model names, retry settings, token budgets, tool limits, and prompt defaults. Keep values safe and disabled by default.

Full and correct source

- src/main/resources/application.properties

- src/main/resources/application-railway.properties

Properties to add

- hyflo.ai.enabled

- hyflo.ai.provider

- hyflo.ai.routing.*

- hyflo.ai.retry.*

- hyflo.ai.tool.max-tool-calls

- hyflo.ai.tool.max-iterations

- hyflo.ai.budget.*

- hyflo.ai.memory.*

Estimated time
30 to 45 minutes

Developing language
Properties

## Phase 1 — Intelligence layer first

This phase comes before platform/ai implementation because the business contracts must drive the runtime, not the reverse.

## Step 1.1

Commit title
feat(intelligence): introduce AI capability layer contracts

Goal
Create a reusable business-facing AI orchestration layer inside intelligence/.

Description
Add capability/ under intelligence/ and create the business entry points that controllers, services, and future batch jobs will call. This avoids pushing prompt orchestration directly into controllers or domain services.

Full and correct source

- src/main/java/dz/sh/trc/hyflo/intelligence/capability/AiCapability.java

- src/main/java/dz/sh/trc/hyflo/intelligence/capability/FlowAnalysisCapability.java

- src/main/java/dz/sh/trc/hyflo/intelligence/capability/CrisisAssessmentCapability.java

- src/main/java/dz/sh/trc/hyflo/intelligence/capability/NetworkInsightCapability.java

Implementation notes

- Use existing HyFlo service naming conventions.

- These classes must depend on ports, not on provider SDKs.

- Keep method signatures DTO-oriented and consistent with the rest of the codebase.

Estimated time
1.5 to 2.5 hours

Developing language
Java

## Step 1.2

Commit title
feat(intelligence-flow): add flow AI port and integrate capability entry point

Goal
Connect the first concrete AI use case to the existing business layer without changing endpoint style.

Description
Create the flow-specific AI port inside intelligence/flow/port/ and wire the capability into the existing flow intelligence service path. Do not create a new endpoint format; reuse the controller/service/DTO pattern already present in HyFloAPI.

Full and correct source

- src/main/java/dz/sh/trc/hyflo/intelligence/flow/port/FlowAnomalyAgentPort.java

- src/main/java/dz/sh/trc/hyflo/intelligence/flow/service/FlowAnomalyService.java or the existing flow intelligence service class

- src/main/java/dz/sh/trc/hyflo/intelligence/flow/dto/**

- src/main/java/dz/sh/trc/hyflo/intelligence/flow/controller/** only if a controller already exists and needs wiring

Implementation notes

- Keep existing endpoint URI style untouched.

- Reuse existing response DTO patterns.

- No direct SDK call from controller or service.

Estimated time
2 to 3 hours

Developing language
Java

## Step 1.3

Commit title
feat(intelligence-crisis-network): add crisis and network AI ports

Goal
Prepare the other two business AI entry points before introducing the shared AI runtime.

Description
Mirror the flow pattern for crisis and network. This keeps the architecture symmetrical and prevents platform/ai from becoming flow-specific.

Full and correct source

- src/main/java/dz/sh/trc/hyflo/intelligence/crisis/port/CrisisAgentPort.java

- src/main/java/dz/sh/trc/hyflo/intelligence/network/port/NetworkInsightAgentPort.java

- src/main/java/dz/sh/trc/hyflo/intelligence/crisis/service/**

- src/main/java/dz/sh/trc/hyflo/intelligence/network/service/**

Implementation notes

- Only add ports and capability integration points.

- Do not implement model clients here.

- Keep controllers unchanged unless required for injection.

Estimated time
2 to 3 hours

Developing language
Java

## Step 1.4

Commit title
feat(intelligence-assistant): add assistant module skeleton with existing API standards

Goal
Prepare the conversational entry point using the same controller/DTO/service conventions as the rest of the API.

Description
Introduce the assistant package in intelligence/assistant/ with controller, DTO, service, and port layers. This commit is a skeleton only; runtime execution will come later in platform/ai.

Full and correct source

- src/main/java/dz/sh/trc/hyflo/intelligence/assistant/controller/AssistantController.java

- src/main/java/dz/sh/trc/hyflo/intelligence/assistant/dto/AssistantRequestDTO.java

- src/main/java/dz/sh/trc/hyflo/intelligence/assistant/dto/AssistantResponseDTO.java

- src/main/java/dz/sh/trc/hyflo/intelligence/assistant/service/OperatorAssistantService.java

- src/main/java/dz/sh/trc/hyflo/intelligence/assistant/port/AssistantAgentPort.java

Implementation notes

- Follow the same endpoint annotation and response structure already used in other HyFlo controllers.

- No WebSocket or streaming implementation yet.

Estimated time
2 to 3 hours

Developing language
Java

## Phase 2 — Create platform/ai foundation

The repository already uses platform/ for technical capabilities, so AI belongs there as a sibling technical module, not under configuration/ and not inside intelligence/.

## Step 2.1

Commit title
feat(platform-ai-core): create ai module core contracts and configuration layer

Goal
Introduce the AI runtime root package and its core contracts.

Description
Create platform/ai/ with the minimal core objects: request, response, context, enums, and configuration classes. This commit must not yet implement retries, routing, tools, or memory.

Full and correct source

- src/main/java/dz/sh/trc/hyflo/platform/ai/agent/AgentPort.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/agent/AgentRequest.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/agent/AgentResponse.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/agent/AgentContext.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/config/AiPlatformAutoConfig.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/config/AiProperties.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/config/AgentConfig.java

Implementation notes

- AiProperties must bind to hyflo.ai.*.

- Keep Spring wiring in config/ only.

- No business rules here.

Estimated time
2 to 3 hours

Developing language
Java

## Step 2.2

Commit title
feat(platform-ai-strategy): add agent strategy layer and slim executor

Goal
Prevent the future AgentExecutor from becoming a god class.

Description
Implement strategy-based execution for stateless analysis, tool-calling, and conversational flows. AgentExecutor becomes an orchestrator that delegates to AgentStrategyRegistry.

Full and correct source

- src/main/java/dz/sh/trc/hyflo/platform/ai/agent/AgentExecutor.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/agent/strategy/AgentStrategy.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/agent/strategy/AgentStrategyRegistry.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/agent/strategy/StatelessAnalysisStrategy.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/agent/strategy/ToolCallingStrategy.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/agent/strategy/ConversationalStrategy.java

Implementation notes

- Use constructor injection only.

- Strategies must depend on ports/adapters, never on controllers.

- Keep method contracts DTO-safe and testable.

Estimated time
3 to 4 hours

Developing language
Java

## Step 2.3

Commit title
feat(platform-ai-model): add provider adapters and Spring AI bridge

Goal
Create the provider abstraction layer without coupling business logic to one LLM vendor.

Description
Introduce LLMClientPort plus the first Spring-AI-backed adapter. If local fallback is planned, create an Ollama adapter contract now, even if not fully activated.

Full and correct source

- src/main/java/dz/sh/trc/hyflo/platform/ai/model/LLMClientPort.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/model/SpringAiLLMAdapter.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/model/OllamaLLMAdapter.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/config/SpringAiClientConfig.java

Implementation notes

- SpringAiLLMAdapter is the default.

- Do not expose provider classes outside platform/ai/model/.

- Keep request and response conversion internal to the adapter.

Estimated time
3 to 4 hours

Developing language
Java

## Step 2.4

Commit title
feat(platform-ai-routing): add model router and routing rules

Goal
Allow model selection by capability and execution type from day one.

Description
Add a routing abstraction that selects a model from the request context, agent type, and routing hint. This commit keeps the routing logic centralized and prevents provider selection from leaking into services.

Full and correct source

- src/main/java/dz/sh/trc/hyflo/platform/ai/routing/ModelRouter.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/routing/RoutingRule.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/routing/RoutingContext.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/routing/RuleBasedModelRouter.java

- src/main/resources/application.properties

- src/main/resources/application-railway.properties

Implementation notes

- Keep simple rule-based routing first.

- Flow analysis can default to cheaper models.

- Crisis and assistant can target stronger or streaming-capable models.

Estimated time
2 to 3 hours

Developing language
Java + Properties

## Phase 3 — Safety and production behavior

## Step 3.1

Commit title
feat(platform-ai-resilience): add retry, circuit breaker, and fallback model support

Goal
Make LLM execution production-safe.

Description
Wrap the provider adapter with retry, circuit breaker, and fallback resolution. This commit should be isolated because it affects failure behavior but not business flow.

Full and correct source

- src/main/java/dz/sh/trc/hyflo/platform/ai/resilience/AiRetryPolicy.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/resilience/AiCircuitBreaker.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/resilience/AiResilienceDecorator.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/resilience/FallbackModelResolver.java

Implementation notes

- Use exponential backoff.

- Retry only transient failures.

- Throw typed technical exceptions after exhaustion.

Estimated time
3 to 4 hours

Developing language
Java

## Step 3.2

Commit title
feat(platform-ai-tooling): add tool registry, execution engine, and loop limits

Goal
Enable controlled tool-calling while preventing runaway execution.

Description
Introduce the tool system, registry, annotation, executor, and guard. This is where max iterations and max tool calls are enforced.

Full and correct source

- src/main/java/dz/sh/trc/hyflo/platform/ai/tool/AiTool.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/tool/ToolRegistry.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/tool/ToolExecutor.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/tool/ToolExecutionGuard.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/tool/tools/FlowQueryTool.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/tool/tools/CrisisDataTool.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/tool/tools/NetworkTopologyTool.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/tool/tools/AuditEventTool.java

Implementation notes

- Tool classes must delegate to existing application services.

- Do not place repository access directly into tool classes if an existing service already owns the logic.

- Keep tool return payloads compact and schema-safe.

Estimated time
4 to 6 hours

Developing language
Java

## Step 3.3

Commit title
feat(platform-ai-format): add structured output enforcement and correction loop

Goal
Make AI responses parseable and safe for business use.

Description
Add JSON/schema validation and a correction-retry mechanism when the model returns invalid output. This is critical for flow scoring, crisis assessment, and machine-consumable assistant responses.

Full and correct source

- src/main/java/dz/sh/trc/hyflo/platform/ai/format/StructuredOutputEnforcer.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/format/JsonSchemaValidator.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/format/OutputCorrectionPromptBuilder.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/format/ParsedOutput.java

Implementation notes

- Correction retries must be limited.

- Validation should happen before any business mapping.

- No raw Map<String,Object> should leak far beyond this boundary.

Estimated time
3 to 4 hours

Developing language
Java

## Step 3.4

Commit title
feat(platform-ai-guardrail): add context integrity and tool output validation

Goal
Prevent invalid business context and invalid tool payloads from contaminating model reasoning.

Description
Add input and output guardrails, especially entity existence validation and tool result validation. This is where AI safety becomes domain-aware.

Full and correct source

- src/main/java/dz/sh/trc/hyflo/platform/ai/guardrail/GuardrailChain.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/guardrail/InputSanitizer.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/guardrail/OutputContentFilter.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/guardrail/ContextIntegrityValidator.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/guardrail/ToolOutputValidator.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/guardrail/PiiRedactor.java

Implementation notes

- ContextIntegrityValidator must query existing services or repositories already responsible for entity existence.

- Keep validation typed and explicit.

- Do not put business authorization rules here; only AI integrity rules.

Estimated time
3 to 4 hours

Developing language
Java

## Phase 4 — Memory, cost, prompts, observability

## Step 4.1

Commit title
feat(platform-ai-memory): add conversation memory and session isolation

Goal
Support assistant sessions safely without cross-user leakage.

Description
Add short-term memory, persistent memory contracts, session registry, and ownership enforcement. The first pass can keep persistent vector memory disabled if database readiness is not finished.

Full and correct source

- src/main/java/dz/sh/trc/hyflo/platform/ai/memory/ConversationMemory.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/memory/InMemoryConversationMemory.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/memory/PgVectorConversationMemory.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/memory/SessionRegistry.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/memory/SessionIsolationEnforcer.java

Implementation notes

- Start with in-memory active and PgVector behind a property flag.

- Session isolation must fail closed.

- Keep session ownership independent from controller state.

Estimated time
4 to 5 hours

Developing language
Java

## Step 4.2

Commit title
feat(platform-ai-cost): add token budget management and usage tracking

Goal
Control runtime costs before exposing AI widely.

Description
Introduce a budget manager, token tracking, cost policy, and guard behavior for exceeded limits. This should be committed separately because it touches persistence and request orchestration.

Full and correct source

- src/main/java/dz/sh/trc/hyflo/platform/ai/cost/TokenBudgetManager.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/cost/TokenUsageTracker.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/cost/CostPolicy.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/cost/UserBudgetRecord.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/cost/BudgetExceededHandler.java

- src/main/resources/application.properties

- optional DB migration path if the project already uses versioned migrations

Implementation notes

- If Flyway or Liquibase already exists, use it; otherwise keep persistence additions aligned with the current project’s data approach.

- Reserve-then-commit is better than post-fact-only counting.

Estimated time
4 to 5 hours

Developing language
Java + Properties + SQL if migration is introduced

## Step 4.3

Commit title
feat(platform-ai-prompt): add prompt templates and prompt versioning

Goal
Make prompts traceable, testable, and auditable.

Description
Introduce prompt registry, renderer, and version entities so AI behavior can evolve without hidden prompt drift.

Full and correct source

- src/main/java/dz/sh/trc/hyflo/platform/ai/prompt/PromptTemplateRegistry.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/prompt/PromptTemplate.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/prompt/PromptVersion.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/prompt/PromptRenderer.java

- src/main/resources/prompts/flow-anomaly-v1.st

- src/main/resources/prompts/crisis-assessment-v1.st

- src/main/resources/prompts/operator-assistant-v1.st

Implementation notes

- Store prompt ids and versions in the response metadata.

- Do not hardcode large prompts in service classes.

- Keep templates business-readable.

Estimated time
3 to 4 hours

Developing language
Java + Text template files

## Step 4.4

Commit title
feat(platform-ai-observability): add AI metrics, audit logging, and insight persistence

Goal
Make AI execution measurable and support later governance.

Description
Add metrics recording, trace context, AI audit logging, and insight persistence. This should integrate with the existing technical direction of platform/ and not create a separate logging island.

Full and correct source

- src/main/java/dz/sh/trc/hyflo/platform/ai/observability/AiMetricsRecorder.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/observability/AiTraceContext.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/observability/AiAuditLogger.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/observability/AiInsight.java

- src/main/java/dz/sh/trc/hyflo/platform/ai/observability/AiInsightRepository.java

Implementation notes

- Persist promptTemplateId, promptVersion, modelUsed, token counts, latency, and error code.

- Reuse existing audit conventions wherever possible.

Estimated time
3 to 5 hours

Developing language
Java

## Phase 5 — Wire intelligence to AI runtime

## Step 5.1

Commit title
refactor(intelligence-ai): wire capability layer to platform agent executor

Goal
Connect the business use cases to the technical AI runtime through stable ports.

Description
Implement the port adapters so intelligence/capability/** calls AgentPort, not provider-specific code. This is the real seam between business and platform.

Full and correct source

- src/main/java/dz/sh/trc/hyflo/intelligence/capability/**

- src/main/java/dz/sh/trc/hyflo/intelligence/flow/port/**

- src/main/java/dz/sh/trc/hyflo/intelligence/crisis/port/**

- src/main/java/dz/sh/trc/hyflo/intelligence/network/port/**

- src/main/java/dz/sh/trc/hyflo/intelligence/assistant/port/**

- src/main/java/dz/sh/trc/hyflo/platform/ai/agent/**

Implementation notes

- Keep all business DTO mapping inside intelligence/.

- Keep platform/ai/ responses generic enough for reuse, but not exposed directly to controllers.

Estimated time
3 to 4 hours

Developing language
Java

## Step 5.2

Commit title
refactor(intelligence-api): expose AI through existing controller standards only

Goal
Publish AI-backed behavior without changing the API style already used by HyFloAPI.

Description
Update or add controllers only where necessary, using the same endpoint annotation style, DTO naming, validation pattern, and URI conventions already present in the project. No new endpoint envelope format should be introduced.

Full and correct source

- src/main/java/dz/sh/trc/hyflo/intelligence/flow/controller/**

- src/main/java/dz/sh/trc/hyflo/intelligence/crisis/controller/**

- src/main/java/dz/sh/trc/hyflo/intelligence/network/controller/**

- src/main/java/dz/sh/trc/hyflo/intelligence/assistant/controller/**

- src/main/java/dz/sh/trc/hyflo/intelligence/**/dto/**

Implementation notes

- Preserve validation annotations.

- Preserve response DTO discipline.

- Preserve route naming conventions already used across modules.

Estimated time
2 to 4 hours

Developing language
Java

## Phase 6 — Testing and architectural locking

## Step 6.1

Commit title
test(platform-ai): add unit, contract, and simulation coverage

Goal
Make the AI platform testable without live model dependency.

Description
Add unit tests for strategies and guards, contract tests for structured outputs, and simulation tests with fake model responses.

Full and correct source

- src/test/java/dz/sh/trc/hyflo/platform/ai/agent/**

- src/test/java/dz/sh/trc/hyflo/platform/ai/format/**

- src/test/java/dz/sh/trc/hyflo/platform/ai/tool/**

- src/test/java/dz/sh/trc/hyflo/intelligence/**

- test resources for simulated responses

Estimated time
4 to 6 hours

Developing language
Java

## Step 6.2

Commit title
test(architecture): enforce ai dependency rules with ArchUnit

Goal
Prevent future architectural drift.

Description
Lock the separation between intelligence/ and platform/ai/, and between platform/ai/ and domain modules, with architectural tests.

Full and correct source

- src/test/java/dz/sh/trc/hyflo/architecture/AiArchitectureTest.java

Rules to enforce

- intelligence/** may depend on platform/ai/agent/AgentPort, but not on provider adapters.

- platform/ai/** must not depend directly on flow/**, crisis/**, or network/** concrete business packages unless via explicit service/tool boundaries.

- Controllers must not call provider adapters.

Estimated time
1.5 to 2.5 hours

Developing language
Java